## Planning Checklist
Parks and Recreation Department Event Planner
Event Name: |  | event name | First Event Day | 2020-07-04
Tier: |  | Choose Answer | Application Date | 2019-06-01
Attendance/ Day: |  |  | # Set Up Days: | 0
Park Name |  | Choose Answer | # Take Down Days: | 0
Park Status: |  | Choose Answer | Number of Events Days: | 0
Required Item | Received Date | Item Description (permit/contract requirement)ê | Format Required ê | Due Date | 335 |  | Choose Answer
| Checkü | APPLICATION, REVIEW AND CONTRACT | FALSE |  | 364 | 0 | Auditorium Shores - main and middle lawn
X |  | Unified Citywide Special Event Application DEADLINE | ACE Online Application |  |  | 1 | Auditorium Shores - main lawn | Choose Answer | Choose Answer
[6 empty] | 2 | Auditorium Shores - middle lawn | Park In Use | Tier 4
|  | ·If Permit Denied, denial date: |  |  |  | 3 | Brush Square Park | Park Partially Open | Tier 3
|  | ·Deadline to Appeal Denial: | 10 business days from denial |  |  | 4 | ESB Mexican American Cultural Center | Park Minimally Open | Tier 2
|  | ·Deadline for Appeal Team Decision: | 10 business days from appeal |  |  | 5 | Festival Beach | Park Closed | Tier 1
May | Apply | Austin Center for Events - Event Overview Meeting |  |  |  | 6 | Fiesta Gardens - West End and Building
X |  | PARD Event Contract Executed |  |  |  | 7 | Givens Park
X |  | Event Evaluation Matrix (see the evaluation tabs below) | PARD staff completed |  |  | 8 | Palm Park
[6 empty] | 9 | Pan Am Recreation Center
| Checkü | PAYMENT SCHEDULE |  |  |  | 10 | Pease Park
X |  | PARD Event Deposit (25% non-refundable event deposit) |  | 2019-06-15 |  | 11 | Republic Square Park
X |  | PARD Final Balance (30 days prior to event) |  | 2020-06-04 |  | 12 | Sand Beach
[6 empty] | 13 | Vic Mathias Shores - Main Lawn
| Checkü | NOTFICATIONS AND COMMUNICATIONS |  |  |  | 14 | Walter E. Long
May apply |  | Notifications New, alcohol served/sold/byob, ticketed, OR special events at NON-special event locations are required to provide notice. | PARD Form | 2020-03-06 |  | 15 | Waterloo Park
May apply |  | Notification - Waterway Use Water use events notice distributed. | PARD Form | 2020-06-04 |  | 16 | Wooldridge Park
X |  | Notification Signage at Site (sign template available) | Signage Install Date→ | 2020-06-20 |  | 17 | Zilker Park
X |  | Public Website Event Posting - Parks Website | PARD staff completed |  |  | 18 | Zilker Botanical Garden
| Checkü | SITE PLAN | 60-30 DAYS PRIOR |  |  | 19 | Umlauf Sclupture Garden
X |  | Site Plan Finalized (cad-like detailed computer drawing) |  | 2020-05-05 |  | 20 | Zach Scott Theatre
X |  | Site Visit with City Staff | On Site Meeting on/around: | 2020-06-04 |  | 21
| Checkü | INSURANCE CERTIFICATES | 2020-06-04 |  |  | 22
X |  | General Commercial and Auto Liability Insurance Certificate | Copy of Certificate |  |  | 23
May apply |  | Liquor Liability (public events, or where alcohol is sold) | Copy of Certificate |  |  | 24
May apply |  | Moonwalks/Rockwalls - (NO water slides, no trains) | Copy of Provider's Certificate |  |  | 25
None. |  | Fireworks/pyrotechnics(insurance specs per AFD) | Copy of Provider's Certificate |  |  | 26
| Checkü | SAFETY PLANS | 2020-06-04 |  |  | 27
X |  | EMS (medical) Services/Plan | Copy of provider contract or plan. |  |  | 28
X |  | Public Safety Plan | Template Available |  |  | 29
X |  | Fire Department Inspection afdspecialevents@austintexas.gov | Pay AFD fees. |  |  | 30
X |  | Fire - Emergency Exit Signage (white background/red letters) | Approx 7' or higher over gates. Must be lit after dark. |  |  | 31
X |  | Inclement Weather Plan | Template Available - May be integrated into safety plan.
na |  | Water Safety Plan Approval | Template Available
na |  | City Council Approval of a swimming event (Lady Bird Lake) | City Council Action Item
| Checkü | LOGISTICS AND SITE OPERATIONS | 2020-06-04
X |  | Event Contact List | PARD Form
X |  | Fencing Contract (mandatory with alcohol) | Contract Copy
X |  | Turf Protection Decking/Material Contract Requires PARD APPROVAL | Contract Copy
X |  | Tent contract copy (NO STAKING ALLOWED). Must show provision of water barrels in contract. | Contract Copy
X |  | Portable Toilet and Hand Sanitizer Plan Includes number & type, hand sanitizer installations, & daily service from paved surfaces. | Contract Copy. Minimum number of toilets →: | 0
na |  | Emissions Management Plan (Tier 4)
na |  | Waste Reduction and Management Plan (Tiers 2-4) (Austin Resource Recovery)
X |  | Trash and Recycling Contract/Plan – dumpsters, recycling, trash containers, and grounds/area litter control. Must all be documented in contract - including general surrounding area clean up. | Contract Copy
X |  | Litter control plan Documentation of active litter control plan during event hours (may be fully noted in your trash/recycling plan). | Contract Copy
X |  | Dumpster Contract | Contract Copy Licensed Hauler.
| Checkü | TRANSPORTATION, PARKING AND SHUTTLES | 2020-06-04
May apply |  | Traffic Control Plan Engineered (street closures) | Permit Copy
na |  | Mobility Plan (Tier 4)
X |  | Transportation and Parking Plan | PARD Form Availabe
|  | · Private Parking Garage Approvals and Listing | Approvals from private garages.
|  | · City Garage Request (form) (Palmer, City Hall, OTC and TLC) | City Form
|  | · ADA Parking designated (advertised publicly on website) | Online Verfication
|  | · Shuttle Plan and Schedule | Contract Copy. Online Verification.
|  | · Shuttle route maps (Color, clearly legible and labeled.) | Contract Copy.
|  | · Bike Parking Bike Rack. (City Sponsored events must provide bike rack for 5% of expected attendees.) | Contract Copy, Online Verification.
|  | · Cap Metro Trip Planner posted on Event Website | Online Verfication
|  | Alternative Transportation Messaging Website must discourage neighborhood parking, highlight bike and bus opportunities (suggest posting hike/bike trail maps). | Online Verfication
na |  | DMS Boards activated. (variable message boards) | City of Austin
| Checkü | PERMITS and LICENSES | 2020-06-04
X |  | Sound Permit PARD (10 am to 10 pm if approved by PARD.)
|  | Sound Impact Plan Required if event hosts 7500 or more on any given day. (fees apply) | Copy of Sound Impact Plan.
Alcohol Permit Review (TABC Aplication Signature) ($30)
|  | TABC Permit Approval | Copy of State Permit
|  | Grass Permits for Park | Template Form Available to Complete
|  | Electrical Permit Required for any direct wire ("pigtail") connections, or wire to wire connections. NOT required for SOLE use of a camlock or edison plug systems. | Copy of Permit
|  | Master Electrician's License (valid license date) | Copy of License
|  | Health Permits (Austin Travis County Health Department) TIP! - Organizer must complete the form for all event vendors & submit at once. | Copy of Permits
NONE |  | Pyrotechnics Permit - Austin Fire Department (requires PARD approval if on or fall zone over parkland) | Copy of Permits
NONE |  | NOTICE - Fireworks Notice to Stakeholders | PARD Form
X |  | Building Permit - structures covering 120 sq. ft or that are used for 10 or more people. REFERENCE BUILDING INSPECTION DOCUMENT | Copy of Permits
May apply |  | Tree Permit - required for any event impact that is under a tree canopy or in the critical root zone area. Review by PARD Forestry and /or City Arborist. | Copy of Permit
| Checkü | POST EVENT - PARD ITEMS | 2020-08-03
X |  | Post Event Walk Through | PARD staff completed
X |  | Post Event Final Report | PARD staff completed
X |  | Process and Release Deposit (minus billable expenses /damage) | PARD staff completed
| Checkü | POST EVENT - ORGANIZER ITEMS
Organizer submits future dates in writing and receives approval.
May apply |  | $1/ticket PER DAY submitted with ticket manifest | Manifest from Ticket Company/ Organizer Letter
EMS Report
na |  | Mobility Report (Tier 4)
Waste Report
PLANNING FOR NEXT YEAR
|  | Open application period begins (new events): | ACE Online Application | 2020-08-03
|  | Open application period begins (returning events): | ACE Online Application | 2020-07-05